## Sheet1
| TESTER NAME: Al Kautsar | PROJECT / TEST CYCLE: USER REGISTRATION | TEST PURPOSE: Functional Testing
| TEST DATE: 01 Maret 2024 | TEST PLATFORM: POSTMAN | BUILD ID: -
| LANGUAGE TESTED: Indonesia | DEVICE / BROWSER: -
Test Id | Test Case | Expected Result (dokumentasi) | Actual Result (postman) | Pass/Fail (pass jika actual sama dengan expected) | Test Step | Positive/Negative Case
Test Condition: Verify Functional Login Feature
1 | Success Login, with registered email and password | { "credentials": { "access_token": "cb8b9ddb850b3850ebbb691af02d75bcf7846ac529cc8a990ebb3b d481cc9cdc", "expired_in": 1647003484, "refresh_token": "d62599cc70f81c8f2e726f79f79332b97c6298d7321404fbc0cd9f ed170fcd16" }, "data": "Welcome tester ganteng", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | { "credentials": { "access_token": "6657c66c6d844e622f95ae166e2ba673fe15fe141c20a01ff5943b61155dd2bd", "expired_in": 1708695583, "refresh_token": "30b145a05a695e473874eaab846da4f12e5deab7663964ff116e8e2a4950dc8d" }, "data": "Welcome batch 18", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | Pass | 1. Isi email dan password teregistrasi 2. Klik tombol Send | Positive
|  | status code = 200 | status code = 200
2 | Success Login, Verify that the API response contains all the expected fields | { "credentials": { "access_token": "cb8b9ddb850b3850ebbb691af02d75bcf7846ac529cc8a990ebb3b d481cc9cdc", "expired_in": 1647003484, "refresh_token": "d62599cc70f81c8f2e726f79f79332b97c6298d7321404fbc0cd9f ed170fcd16" }, "data": "Welcome tester ganteng", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | { "credentials": { "access_token": "6657c66c6d844e622f95ae166e2ba673fe15fe141c20a01ff5943b61155dd2bd", "expired_in": 1708695583, "refresh_token": "30b145a05a695e473874eaab846da4f12e5deab7663964ff116e8e2a4950dc8d" }, "data": "Welcome batch 18", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | Pass | 1. Isi email dan password teregistrasi 2. Klik tombol Send | Positive
|  | status code = 200 | status code = 200
3 | Gagal Login dengan email yang tidak terdaftar | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | fail | 1. isi email dan password yang tidak teregistrasi, 2.klik send | negative
|  | status code = 420 | status code = 200
4 | Success Login, Verify that the API response contains the correct data for each field | { "credentials": { "access_token": "cb8b9ddb850b3850ebbb691af02d75bcf7846ac529cc8a990ebb3b d481cc9cdc", "expired_in": 1647003484, "refresh_token": "d62599cc70f81c8f2e726f79f79332b97c6298d7321404fbc0cd9f ed170fcd16" }, "data": "Welcome tester ganteng", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | { "credentials": { "access_token": "1c35fed6d8243be44ae479ca46421849fce64982e4d315262bbdcea2389f0c5f", "expired_in": 1709044714, "refresh_token": "638e849baa98f5de6fe70b98d05ac6dc1c6ab508b74f522c2e4162e09d39d973" }, "data": "Welcome alka", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | pass | 1. Isi email dan password teregistrasi 2. Klik tombol Send | positive
|  | status code : 200 | status code : 200
5 | Success Login, Verify that the API request parameters are correctly passed to the API. | { "credentials": { "access_token": "cb8b9ddb850b3850ebbb691af02d75bcf7846ac529cc8a990ebb3b d481cc9cdc", "expired_in": 1647003484, "refresh_token": "d62599cc70f81c8f2e726f79f79332b97c6298d7321404fbc0cd9f ed170fcd16" }, "data": "Welcome tester ganteng", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | { "credentials": { "access_token": "1c35fed6d8243be44ae479ca46421849fce64982e4d315262bbdcea2389f0c5f", "expired_in": 1709044714, "refresh_token": "638e849baa98f5de6fe70b98d05ac6dc1c6ab508b74f522c2e4162e09d39d973" }, "data": "Welcome alka", "message": "Anda Berhasil Login", "status": "SUCCESS_LOGIN" } | pass | 1. Isi email dan password teregistrasi 2. Klik tombol Send | positive
|  | status code : 200 | status code : 200
6 | Gagal login dengan password yang salah | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | fail | 1. Isi email teregistrasi dan password salah 2. Klik tombol Send | negative
|  | status code : 420 | status code: 200
7 | gagal login dengan email dan password yang belum teregistrasi | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | { "data": "User's not found", "message": "Email atau Password Anda Salah", "status": "FAILED_LOGIN" } | fail | 1. Isi email dan password yang belum teregistrasi 2. Klik tombol Send | negative
|  | status code : 420 | status code : 200
8 | Gagal login dengan email yang tidak valid | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_LOGIN" } | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_LOGIN" } | pass | 1. Isi email yang tidak sesuai dan password 2. Klik tombol Send | negative
|  | status code : 420 | status code : 420
9
Test Id | Test Case | Expected Result | Actual Result | Pass/Fail | Test Step | Positive/Negative Case
Test Condition: Register Feature
1 | Success Register | { "data": "berhasil", "message": "created user!", "status": "SUCCESS_REGISTER" } | { "data": "berhasil", "message": "created user!", "status": "SUCCESS_REGISTER" } | Pass | 1. Mengisi email dengan data valid 2. Mengisi password dengan data valid 3. Mengisi name dengan data valid | Positive
|  | status code = 200 | status code = 200
2 | Failed Register with empty name | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | Pass | 1. Mengisi email dengan data valid 2. Mengisi password dengan data valid 3. name dibiarkan kosong | Negative
|  | status code = 420 | status code = 420
3 | Gagal registrasi dengan email yang sudah terdaftar | { "data": "Email sudah terdaftar, gunakan Email lain", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | { "data": "Email sudah terdaftar, gunakan Email lain", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | pass | 1. mengisi email terdaftar 2. Password diisi 3. Name disisi , 4. klik send | Negative
|  | status code = 420 | status code = 420
4 | gagal registrasi dengan password kosong | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | pass | 1. Email diisi dengan data vallid 2. Password dikosongkan 3. Name diisi 4. klik send | Negative
|  | status code = 420 | status code = 420
5 | gagal registrasi dengan email kosong | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | { "data": "Email/Username/Password tidak boleh kosong", "message": "Gagal Registrasi", "status": "FAILED_REGISTER" } | pass | 1. Email tidak di sisi 2. Password diisi 3. Name diisi 4. klik send | Negative
|  | status code = 420 | status code = 420
6 | gagal registrasi dengan email tidak valid | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_REGISTER" } | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_REGISTER" } | pass | 1. Email diisi dengan tidak valid 2. Password diisi 3. Name diisi 4. klik send | negative
|  | status code = 420 | status code = 420
7 | gagal registrasi dengan email mengandung simbol | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_REGISTER" } | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_REGISTER" } | pass | 1. Email diisi dengan simbol 2. Password diisi 3. Name diisi 4. klik send | negative
|  | status code = 420 | status code = 420
8 | gagal registrasi dengan username mangandung simbol | { "data": "Nama atau password tidak valid", message": "Tidak boleh mengandung symbol", "status": "FAILED_REGISTER" } | { "data": "Password tidak valid", "message": "Tidak boleh mengandung symbol", "status": "FAILED_REGISTER" } | fail | 1. Email diisi 2. Password diisi 3. Name diisi dengan simbol 4. klik send | negative
|  | status code = 420 | status code = 420
9 | gagal registrasi dengan password mangandung simbol | { "data": "Nama atau password tidak valid", message": "Tidak boleh mengandung symbol", "status": "FAILED_REGISTER" } | { "data": "Email tidak valid", "message": "Cek kembali email anda", "status": "FAILED_REGISTER" } | fail | 1. Email diisi 2. Password diisi dengan simbol 3. Name diisi 4. klik send | negative
|  | status code = 420 | status code = 420
10 | gagal registrasi dengan username dan password mangandung simbol | { "data": "Nama atau password tidak valid", message": "Tidak boleh mengandung symbol", "status": "FAILED_REGISTER" } | { "data": "Password tidak valid", "message": "Tidak boleh mengandung symbol", "status": "FAILED_REGISTER" } | fail | 1. Email diisi 2. Password diisi dengan simbol 3. Name diisi denga simbol 4. klik send | negative
|  | status code = 420 | status code = 420
Test Id | Test Case | Expected Result | Actual Result | Pass/Fail | Test Step | Positive/Negative Case
Test Condition: List User Feature
1 | Success get List User, without param | { "data": [ { "email": "barru.kurniawan@gmail.com", "username": "Barru Kurniawan" }, { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 61 }, "status": "SUCCESS_USER_LIST" } | { "data": [ { "email": "barru.kurniawan@gmail.com", "username": "Barru Kurniawan" }, { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 61 }, "status": "SUCCESS_USER_LIST" } | Pass | 1. Hit API List User tanpa param | Positive
2 | Success get List User, with empty email parameter | { "data": [ { "email": "gantengku@gmail.com", "username": "janda ganteng" }, { "email": "gantengku@sdjhs.id", "username": "barru ganteng" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2 }, "status": "SUCCESS_USER_LIST" } | { "data": [ { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" }, { "email": "dwinuritasari@gmail.com", "username": "dwi nurita sari" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2786 }, "status": "SUCCESS_USER_LIST" } | Pass | 1. Kosongkan parameter email 2. klik send | Positive
3 | Success get List User, with empty email and empty username parameter | { "data": [ { "email": "gantengku@gmail.com", "username": "janda ganteng" }, { "email": "gantengku@sdjhs.id", "username": "barru ganteng" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2 }, "status": "SUCCESS_USER_LIST" } | { "data": [ { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" }, { "email": "dwinuritasari@gmail.com", "username": "dwi nurita sari" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2786 }, "status": "SUCCESS_USER_LIST" } | Pass | 1. Kosongkan parameter email 2. Kosongkan parameter username 3. klik send | Positive
4 | Success get List User, with email value and empty username parameter | { "data": [ { "email": "gantengku@gmail.com", "username": "janda ganteng" }, { "email": "gantengku@sdjhs.id", "username": "barru ganteng" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2 }, "status": "SUCCESS_USER_LIST" } | { "data": [ { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" }, { "email": "dwinuritasari@gmail.com", "username": "dwi nurita sari" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2786 }, "status": "SUCCESS_USER_LIST" } | pass | 1. Mengisi email valid terdaftar 2. Kosongkan parameter username 3.klik send | Positive
5 | Success get List User, with email value and valid username parameter | { "data": [ { "email": "gantengku@gmail.com", "username": "janda ganteng" }, { "email": "gantengku@sdjhs.id", "username": "barru ganteng" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2 }, "status": "SUCCESS_USER_LIST" } | { "data": [ { "email": "sitampan@gmail.com", "username": "tampan berani" }, { "email": "deinuritasari@gmail.com", "username": "dwi nurita sari" }, { "email": "dnrinnes@gmail.com", "username": "innes" }, { "email": "hidayatiyulvi@gmail.com", "username": "yulvi" }, { "email": "dwinuritasari@gmail.com", "username": "dwi nurita sari" } ], "message": "List of registered users", "pagination": { "current_page": 1, "limit_per_page": 5, "total_data": 2786 }, "status": "SUCCESS_USER_LIST" } | pass | 1. Mengisi email valid terdaftar 2. Mengisi username valid terdaftar sesuai email 3.klik send | Positive

## Sheet2
Test Id | Test Case | Expected Result | Actual Result | Pass/Fail | Test Step | Positive/Negative Case
Test Condition: Register Feature
1 | Success Register | Menampilkan pop up Success Register | Menampilkan pop up Success Register | Pass | 1. Mengisi email dengan data valid 2. Mengisi password dengan data valid 3. Mengisi name dengan data valid | Positive
2 | Failed Register with empty name | Menampilkan pop up Failed Register | Menampilkan pop up Failed Register | Pass | 1. Mengisi email dengan data valid 2. Mengisi password dengan data valid 3. name dibiarkan kosong | Negative